Building Pathways Project – Business and ICT/Computing Curriculum Group

Proposed Project Activity Plan 2004-2005

| Project | Partners | Activity needed for Project development | Timescale for development | Participations and responsibility |
| --- | --- | --- | --- | --- |
| - Development of ‘Student Ambassadors’ programme to support aspiration raising activities with Level 3 learners on Business and Computing programmes in 4/5 partner colleges with at least one programme of support offered to each college | - Named staff in Sheffield College, RCAT, Rother Valley College, Doncaster College and Chesterfield College - Named teaching/admission tutors in Schools of Business and CMS in Sheffield Hallam University and any other HE providers as identified by partners - Named admission officers in SHU Schools - Hallam Volunteering Manager and relevant colleagues - Named staff from SHU Students Services Centre - Aimhigher coordinators - Business and Education-SYorks | - Define aims and objectives of the Project - Facilitate meeting/communications between partners to define role of student ambassadors - Identify student/tutor groups for targeted activity and number of students to be involved - Develop links with Hallam Volunteering to develop a defined role for ambassadors - Identify number of Ambassadors to be recruited with shared agreement on limit of numbers - Work with partners to develop recruitment strategy for ambassadors - Agree payment and costs of ambassadors - Liaise with Aimhigher coordinators in partner centres - Draw up detailed timetable for activity and confirm with all partners for three ‘ambassador visit’ days in the student academic year, namely in November/December, February/March, May - Ensure planned activities feature as part of college student’s tutorial programme - HV to recruit students to work as ‘ambassadors’ with support of BP, SSC, Schools in SHU as necessary - Facilitate regular communication between partners to ensure programme of activity will be implemented including curriculum group meetings in September, January, April, June - Develop monitoring form to record activity and evaluation including establishment of baseline for measuring outcomes | Activities a-f June to September 2004 June – September June- July 2004 June – September 2004 September 2004 ongoing August-September 2004 | Building Pathways Project worker All partners Building Pathways coordinator BP project worker with partners College tutors Hallam volunteering Building Pathways team BP with partners |
| - Development of at least 1 Master-class for 1 target group of learners in each centre |  | - Agree format of development with BE-SY who will have lead responsibility for the development. - Identify with partners appropriate timescale for development of activities to fit within the timetable of the target group - Identify groups and student numbers for involvement in the classes - Ensure appropriate staff within organisations are informed and involved at an early stage - Link with Aimhigher coordinators in identified centres to share knowledge of the planned activity - Implement plan of activity - Ensure monitoring process of activity is in place | June – September 2004 September 2004 – June 2005 September 2004 | BESY and BP Partners BESY BESY & BP |
| c. Development of materials identifying progression routes for learners from Level 3 programmes to He provision across the sub-region |  | - Ensure clarity of progression opportunities - Agree with partners on the format and content of materials and Agree on distribution process of information on progression routes - Agree timetable of identified Open days and support mechanisms for ensuring learner attendance- linking with master class programme as appropriate | June – October 2004 Sept – Dec 2004 June to December 2004 | BP Project workers All Partners |